## Slide 1: Alternative Delivery
Rudy E. Kilian
A collaborative approach to delivering the largest thickening and dewatering facilities in the US – a design-build journey.
TACWA Meeting Houston, TX / August 18, 2025

## Slide 2: A spectrum of delivery methods is used in the W/WW market
Fixed Price
Design-Build
Range of Delivery Models
Early Cost Certainty/Budget Control
More Design Control
Reduced Risk to Owner
Shorter Schedule
CMAR
Design-Bid-Build
Progressive
Design-Build
Notes: Talk through CSP as a variation of DBB.

## Slide 3: Design-Bid-Build (DBB)
Key Characteristics and Considerations
  Traditional approach for the W/WW market.
  Appropriate when early delivery is not required.
  Low-bid selection without regard to contractor capabilities.
  Owner controls design development
  Complex projects can lead to higher risks for the owner.
  Can procure under Competitive Sealed Proposal (CSP) to select on a best-value basis.
Legend
Working Relationship
Contractual Relationship
Owner
Contractor
Designer
Selection following design completion
Selection at beginning of design

## Slide 4: Construction Manager at-Risk (CMAR)
Legend
Working Relationship
Contractual Relationship
Owner
Contractor
Designer
Selection at ~30% to ~60% design
Selection at beginning of design
SJRA
Contractor
Designer
Legend
Working Relationship
Contractual Relationship
Selection at ~30% to ~ 60% design
Arranged Relationship
Selection at beginning of design
Key Characteristics and Considerations
  Used frequently over the last 10+ years in the W/WW market.
  CMAR selection based on price +qualifications.
  Cost modeling leads to earlier cost certainty.
  GMP negotiated prior to construction; off-ramp available if agreement not reached.
  Can reduce the overall length of the project.
  Project costs are typically higher than DBB, but risks are lowered.

## Slide 5: Fixed Price Design Build (FPDB) Progressive Design-Build (PDB)
Legend
Working Relationship
Contractual Relationship
Owner
Designer/ Builder
Selection at ~1-5% design
Key Characteristics and Considerations
  Increasingly used in the U.S. W/WW market for complex projects.
  2-phase delivery with the ability for design collaboration. (PDB)
  GMP negotiated prior to construction; off-ramp available if agreement not reached. (PDB)
  Allows for earlier project completion.
  Can include a performance guarantee.

## Slide 6: Delivery method comparison
 | Design-Bid-Build | CMAR | Progressive Design-Build
Early Cost Certainty |  |  | 
Schedule Flexibility |  |  | 
Design Control |  |  | 
Risk Allocation |  |  | 
Project Quality |  |  | 
Relative Ranking Legend
Best meets criteria
Partially meets criteria
Least meets criteria

## Slide 7: A tool for internal consensus decision-making
DBIA - Rocky Mountain Region
Notes: Blake – BIM was also used to help obtain internal consensus.

## Slide 8: KCMO Solids Improvement Project Owner’s Advisor for fixed Price (turned into progressive) Design-Build

## Slide 9: 12 months of design decisions

## Slide 10
Blue River Wastewater Treatment Facility
Kansas City, MO
CLICK TO LEARN MORE
CAROLLO | 10

## Slide 12: And then the DB Teams came in…

## Slide 13
Central District Wastewater Treatment Plant (CDWWTP)
Thickening & Dewatering Project Model/Pictures

## Slide 14: Building Design was optimized for Weight and Cost

## Slide 15: CDWWTP Thickening & Dewatering Project Model/Pictures

## Slide 16: CDWWTP Thickening & Dewatering Project Model/Pictures

## Slide 17: CDWWTP Thickening & Dewatering Project

## Slide 18
Central District Wastewater Treatment Plant
Thickening & Dewatering Building
Construction
Model - Water Booster Tanks & Influent Piping vs Similarly Installed

## Slide 19
South District Wastewater Treatment Plant (SDWWTP)
Thickening & Dewatering Model/Pictures

## Slide 20: SDWWTP Thickening & Dewatering Project Model/Pictures
Pump Room
Model vs PUMPS: WAS Grinder & WAS Feed - DSL Grinder & DSL Feed

## Slide 21: SDWWTP Thickening & Dewatering Project Model/Pictures

## Slide 22: SDWWTP Thickening & Dewatering Project Pictures

## Slide 23: SDWWTP Thickening & Dewatering Project Model/Pictures

## Slide 24
SDWWTP
Thickening & Dewatering Project Model/Pictures

## Slide 25: Summary
Alternative Delivery can:
  Reduce the time to beneficial occupancy
  Provide early price certainty for owner
  Provide more optimized (size, cost) facility
Alternative Delivery (Fixed Price Design Build) can also:
  Reduce the input from staff and operations in the final product
  Provide materials or suppliers that may not be of common use by the Utility